## Executive Summary
Enterprise Multi-Agent Daily Rollup — 2026-09-08
Data Source: Ganesh's PostgreSQL Knowledge Base (Supabase) ¦ Generated: 2026-09-08 12:09:56
Team Member | Assignments Open | Delivered | Late | Concepts Demonstrated | Concepts Confused/Partial | Mentor Feedback
Dakshinya Nachimuthu | 28 | 6 | 2 | 0 | 19 | 41
Ganesh Krishna | 31 | 3 | 0 | 0 | 3 | 25
Himaya Perumal | 25 | 4 | 2 | 0 | 16 | 44
Cohort Total

## Deliverables & Tasks
Trainee | Task Description | Status | Due Date | Delivered Date | Was Late? | As of Session
Ganesh Krishna | Formulate one or two strong hypotheses to validate with the first model answering what features drive customer churn | GIVEN | 2026-07-03 | - | NO | 2026-07-02
Himaya Perumal | try embeddings, plot them, and build a model using embeddings | DELIVERED | 2026-07-03 | 2026-07-08 | YES | 2026-07-08
Ganesh Krishna | Train the model with balanced/equal proportions of churn and not churn using a smaller training set and present the results | GIVEN | 2026-07-04 | - | NO | 2026-07-03
Dakshinya Nachimuthu | present architecture diagram explaining problem understanding, vision, and agent design for graph pipeline output classification | DELIVERED | 2026-07-14 | 2026-07-14 | NO | 2026-07-14
Ganesh Krishna | present architecture diagram showing number of agents, purpose of each agent, and tool access/commands for the Excel agent use case | GIVEN | 2026-07-14 | - | NO | 2026-07-13
Ganesh Krishna | Complete the Excel data extraction layer preserving format and styling and demonstrate the post-extraction data structure output | IN_PROGRESS | 2026-07-15 | - | NO | 2026-07-16
Himaya Perumal | run setup script, complete MCP extraction using the Zomato dataset, commit all code to Git, and present the diagram | GIVEN | 2026-07-15 | - | NO | 2026-07-14
Himaya Perumal | demonstrate MCP usage, methods, authentication, and file retrieval for the Zomato dataset | GIVEN | 2026-07-15 | - | NO | 2026-07-15
Dakshinya Nachimuthu | build and demonstrate the first MVP of the agent workflow with must-have features | IN_PROGRESS | 2026-07-16 | - | NO | 2026-07-15
Himaya Perumal | learn Git concepts and what problems it solves for operations | GIVEN | 2026-07-16 | - | NO | 2026-07-15
Himaya Perumal | Learn Git to answer questions tomorrow | GIVEN | 2026-07-16 | - | NO | 2026-07-15
Ganesh Krishna | show the JSON extraction structure and render-back-to-Excel comparison | DELIVERED | 2026-07-17 | 2026-07-17 | NO | 2026-07-17
Ganesh Krishna | test 7 scenarios across normal, edge, and negative test case buckets for each of the three Excel editing operations and provide a full test report | IN_PROGRESS | 2026-07-18 | - | NO | 2026-07-22
Ganesh Krishna | research alternative ways for LLMs to consume Excel files such as Base64 format and URLs | GIVEN | 2026-07-18 | - | NO | 2026-07-17
Dakshinya Nachimuthu | read write-up on supervisors, agents, and the system architecture over the weekend to prepare for questions on Monday | IN_PROGRESS | 2026-07-21 | - | NO | 2026-07-20
Himaya Perumal | set up a cron job to schedule the data pipeline daily at 2 AM and ensure automated recovery | GIVEN | 2026-07-21 | - | NO | 2026-07-20
Dakshinya Nachimuthu | Implement caching in the retrieval pipeline, remove unnecessary code, and demonstrate embedding storage and cache hits live | DELIVERED | 2026-07-22 | 2026-07-22 | NO | 2026-07-22
Dakshinya Nachimuthu | double check how Scroll API works versus standard retrieval chunk limits and explain the exact implementation | GIVEN | 2026-07-22 | - | NO | 2026-07-21
Dakshinya Nachimuthu | Create a chunking evaluation framework using first principles and evaluate retrieval results with an LLM | GIVEN | 2026-07-22 | - | NO | 2026-07-21
Ganesh Krishna | build a UI for uploading Excel files, LLM-based editing, re-rendering the file, and highlighting edited cells in red | GIVEN | 2026-07-22 | - | NO | 2026-07-17
Ganesh Krishna | build a simple UI to upload Excel files, have an LLM perform edits, and re-render the file with edited cells color-coded in red | GIVEN | 2026-07-22 | - | NO | 2026-07-17
Himaya Perumal | implement caching for document embeddings and track cache hits and caching metrics | DELIVERED | 2026-07-22 | 2026-07-24 | YES | 2026-07-24
Himaya Perumal | Create a chunking evaluation framework using first principles and evaluate retrieval results with an LLM | GIVEN | 2026-07-22 | - | NO | 2026-07-21
Himaya Perumal | fix RAG retrieval errors and demonstrate it tomorrow | IN_PROGRESS | 2026-07-22 | - | NO | 2026-07-21
Dakshinya Nachimuthu | research context engineering and conduct comprehensive retrieval pipeline experiments across varied use cases and edge cases, evaluating retrieval versus LLM layer failures | GIVEN | 2026-07-23 | - | NO | 2026-07-23
Dakshinya Nachimuthu | conduct experiments evaluating retrieval response quality and completeness with and without Scroll API, and accuracy with and without re-rankers | GIVEN | 2026-07-23 | - | NO | 2026-07-22
Dakshinya Nachimuthu | Research methodologies for selecting top-K chunks in retrieval and explain the rationale for choosing the K value | GIVEN | 2026-07-23 | - | NO | 2026-07-22
Dakshinya Nachimuthu | Explain how the LLM knows not to hallucinate and handles missing information when retrieved chunks do not contain the answer | GIVEN | 2026-07-23 | - | NO | 2026-07-22
Dakshinya Nachimuthu | Read about context engineering and conduct retrieval pipeline evaluation experiments covering 4-5 distinct test scenarios including edge cases | GIVEN | 2026-07-23 | - | NO | 2026-07-23
Dakshinya Nachimuthu | Implement training history retrieval (day-wise and all-time) and report generation skills using Scroll API | GIVEN | 2026-07-23 | - | NO | 2026-07-22
Ganesh Krishna | find all answers to technical questions about the architecture and prepare to defend the solution for presentation | GIVEN | 2026-07-23 | - | NO | 2026-07-17
Himaya Perumal | Understand how embedding caches are built and stored, and implement document embedding caching properly | GIVEN | 2026-07-23 | - | NO | 2026-07-22
Dakshinya Nachimuthu | study RAG notes, thoroughly understand the code and experiments, and prepare for questions on Monday evening | GIVEN | 2026-07-27 | - | NO | 2026-07-24
Ganesh Krishna | Convert the Excel agent workflow implementation into LangGraph | GIVEN | 2026-07-27 | - | NO | 2026-07-27
Dakshinya Nachimuthu | demonstrate and show experiment results | GIVEN | 2026-07-28 | - | NO | 2026-07-27
Himaya Perumal | explain how to scale the system, the cost, expected savings, and scaling plan | GIVEN | 2026-07-28 | - | NO | 2026-07-27
Dakshinya Nachimuthu | Answer the technical question assigned in the previous meeting | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Dakshinya Nachimuthu | present architecture from first principles with nice-to-haves and demonstrate the working of the 2 XLs | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Dakshinya Nachimuthu | Read and interpret results of the three retrieval experiments comparing scroll API and standard retrieval with rerankers, evaluate quality, caveats, and determine the winner to present | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Ganesh Krishna | Read about agent sandboxes and working trees in Git, and create a sandbox environment for Excel file editing and rendering | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Ganesh Krishna | Research how diffs work and investigate generating and rendering JSON diffs for Excel file edits | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Himaya Perumal | Define the role, purpose, uniqueness, must/should/could-haves for all three agents, re-evaluate metadata user scoping, and present an agent design roadmap | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Himaya Perumal | Define the role, purpose, unique features, roadmap, and must-have, should-have, and could-have capabilities for all three agents | GIVEN | 2026-07-29 | - | NO | 2026-07-28
Dakshinya Nachimuthu | Fix batch size and present 3 retrieval experiments (Scroll API with reranker, Scroll API without reranker, and without Scroll API with reranker) with evidence showing whether the reranker helps | GIVEN | 2026-07-30 | - | NO | 2026-07-29
Dakshinya Nachimuthu | Run retrieval experiment with top-K vector search alone without reranker and present results | GIVEN | 2026-07-30 | - | NO | 2026-07-29
Dakshinya Nachimuthu | Present the specific value added by the reranker to the Scroll API with response and chunk evidence comparing with and without Scroll API | GIVEN | 2026-07-30 | - | NO | 2026-07-29
Ganesh Krishna | Implement Excel diff tracking by comparing request backups to display old vs new rows and request user confirmation before changes | GIVEN | 2026-07-30 | - | NO | 2026-07-29
Himaya Perumal | Rework the agent workflow and MoSCoW framework design with personalized user-scoped skills, user scoping instead of database RLS, Word transcript input, and first principles RAG framing, and present it tomorrow | GIVEN | 2026-07-30 | - | NO | 2026-07-29
Himaya Perumal | Rework RAG system design from first principles incorporating feedback and present it tomorrow | GIVEN | 2026-07-30 | - | NO | 2026-07-29
Dakshinya Nachimuthu | Fix pipeline latency by adjusting batch size and using native Qdrant vector search, and run experiment 3 without Scroll API using provided test cases | GIVEN | 2026-08-03 | - | NO | 2026-07-29
Ganesh Krishna | Fork repository, understand reranking experiments, build an LLM reranker and agent graph with custom Qdrant collection and metadata design, and conduct experiments | GIVEN | 2026-08-03 | - | NO | 2026-07-29
Himaya Perumal | Rework presentation slides for Monday, detailing mistakes, what was tried, what failed, how problems were solved, chunking strategy comparison, Qdrant metadata filtering, and key learnings | GIVEN | 2026-08-03 | - | NO | 2026-07-31
Himaya Perumal | Redesign the architecture diagram and slides into System 1 (ETL pipeline) and System 2 (agents and tools), removing AI jargon and UI clutter | GIVEN | 2026-08-03 | - | NO | 2026-07-31
Himaya Perumal | Present an understanding of prompt revisions, why previous prompts failed, improvements made, and test results along with newly normalized and re-chunked document data | GIVEN | 2026-08-05 | - | NO | 2026-08-04
Dakshinya Nachimuthu | Present results and details of retrieval pipeline evaluation experiments | DELIVERED | 2026-08-10 | 2026-08-12 | YES | 2026-08-12
Dakshinya Nachimuthu | Present the final evaluation report and retrieval experiment results (including P2 and P4 mechanisms, context engineering, and the framework table) on Monday | DELIVERED | 2026-08-10 | 2026-08-12 | YES | 2026-08-12
Dakshinya Nachimuthu | Explain why keyword density weight is set to 0.05 instead of 0.50 in the custom reranker when metadata filtering already handles speaker and date matches | GIVEN | 2026-08-13 | - | NO | 2026-08-12
Dakshinya Nachimuthu | Investigate from code and clarify the Pipeline 3 retrieval mechanism, the re-ranker execution workflow, and the rationale for setting keyword density to 0.05 versus 0.50 | GIVEN | 2026-08-13 | - | NO | 2026-08-12
Ganesh Krishna | Create a checklist of the implementation plan showing completed items and current progress, and present it tomorrow | GIVEN | 2026-08-13 | - | NO | 2026-08-12
Dakshinya Nachimuthu | Write a Python script to connect and migrate existing collections to Qdrant cloud cluster, and present knowledge base system design defining Postgres vs Qdrant usage | GIVEN | 2026-08-17 | - | NO | 2026-08-17
Dakshinya Nachimuthu | Modularize System 1, create an API wrapper, reorganize repository with a legacy folder, and push to GitHub | GIVEN | 2026-08-18 | - | NO | 2026-08-18
Ganesh Krishna | Design and build the pipeline for the knowledge base and present the initial version or architecture design tomorrow | GIVEN | 2026-08-18 | - | NO | 2026-08-17
Ganesh Krishna | Build an end-to-end pipeline to extract Word transcripts, run normalization to JSONL, chunk/embed, and push to Qdrant collection | GIVEN | 2026-08-18 | - | NO | 2026-08-18
Himaya Perumal | Create custom skills, remove the Grok API key, and demonstrate skill execution using P4 | GIVEN | 2026-08-18 | - | NO | 2026-08-18
Himaya Perumal | Demonstrate mentor and manager agents working from Dakshinya's RAG pipeline | GIVEN | 2026-08-18 | - | NO | 2026-08-17
Himaya Perumal | Build and demonstrate the mentor and manager agents working from Dakshinya's RAG system, implementing harness engineering, context engineering, prompt engineering, and tool calling | GIVEN | 2026-08-18 | - | NO | 2026-08-17
Himaya Perumal | Remove duplicates in Qdrant collection, create new collection with updated documents, and present progress | GIVEN | 2026-08-19 | - | NO | 2026-08-18
Dakshinya Nachimuthu | investigate and fix training graph/score of 1.0, plot probability distributions to find optimal cutoff threshold, and show cross-validation results in presentation | GIVEN | Unspecified | - | NO | 2026-07-03
Dakshinya Nachimuthu | Refactor and modularize the RAG codebase into three distinct FastAPI services: ingestion into Qdrant, retrieval with modular re-ranking and prompt builder, and evaluation | GIVEN | Unspecified | - | NO | 2026-08-17
Dakshinya Nachimuthu | read about what meta agents are, what meta tasks mean in AI agents, and why LangGraph is superior | GIVEN | Unspecified | - | NO | 2026-07-10
Dakshinya Nachimuthu | start building models (Random Forest / XGBoost) and look into SHAP / TreeSHAP for feature importance interpretation | DELIVERED | Unspecified | 2026-07-03 | NO | 2026-07-03
Dakshinya Nachimuthu | Extend retrieval test cases to 5-7 distinct questions including metadata and date filtering | DELIVERED | Unspecified | 2026-08-12 | NO | 2026-08-12
Dakshinya Nachimuthu | build a skill and conduct experiments on it | GIVEN | Unspecified | - | NO | 2026-07-24
Dakshinya Nachimuthu | initialize the Git repository and send an invitation | GIVEN | Unspecified | - | NO | 2026-07-15
Ganesh Krishna | plot and inspect training loss graph to verify against overfitting or underfitting | GIVEN | Unspecified | - | NO | 2026-07-03
Ganesh Krishna | integrate the LLM with the Excel editing workflow to run scripts dynamically and test using natural language test scenarios | IN_PROGRESS | Unspecified | - | NO | 2026-07-23
Ganesh Krishna | stress test multi-document upload handling (2, 3, 4 documents), edit and format resolution, and identify failure points | GIVEN | Unspecified | - | NO | 2026-07-27
Ganesh Krishna | integrate the LLM with the Excel editing workflow to handle cell edits, row insertions, and search tool calls | DELIVERED | Unspecified | 2026-07-24 | NO | 2026-07-24
Ganesh Krishna | Fork repository, study the training material, understand reranking, and build an LLM reranker and agent graph to conduct experiments | GIVEN | Unspecified | - | NO | 2026-07-29
Ganesh Krishna | experiment with dataset size and try XGBoost to account for class imbalance | GIVEN | Unspecified | - | NO | 2026-07-03
Ganesh Krishna | integrate the Excel editing workflow with AI agents and demonstrate the complete agent flow | GIVEN | Unspecified | - | NO | 2026-07-22
Ganesh Krishna | include a timeline slide with the start date and number of days in the weekly progress presentation | GIVEN | Unspecified | - | NO | 2026-07-08
Ganesh Krishna | Rework presentation slides to capture specific technical learnings, tool calling with openpyxl, routing, and proper slide structure without cope language | GIVEN | Unspecified | - | NO | 2026-07-31
Ganesh Krishna | research and understand practically how AI agent orchestration frameworks work | GIVEN | Unspecified | - | NO | 2026-07-10
Ganesh Krishna | Store uploaded Excel file structure and content in a database for retrieval and stress test edge cases with multiple simultaneous document uploads | GIVEN | Unspecified | - | NO | 2026-07-27
Ganesh Krishna | Add timeline and weekly progress slides to the presentation | GIVEN | Unspecified | - | NO | 2026-07-08
Ganesh Krishna | Create a system capability document (PRD) for the AI Excel editing system, clean up the codebase, add README files, comment code, and push all changes to remote | GIVEN | Unspecified | - | NO | 2026-08-04
Ganesh Krishna | perform multivariate analysis including balance, age, and correlations with labels in EDA | DELIVERED | Unspecified | 2026-07-03 | NO | 2026-07-03
Ganesh Krishna | find a way to mitigate token consumption for repeated Excel edits without re-reading the full context every time | GIVEN | Unspecified | - | NO | 2026-07-17
Ganesh Krishna | answer whether class imbalance affects model inference | GIVEN | Unspecified | - | NO | 2026-07-03
Himaya Perumal | Test document embedding caching, verify cache hits, and demonstrate the percentage of cache hits from previous documents | GIVEN | Unspecified | - | NO | 2026-07-23
Himaya Perumal | automate MCP data ingestion to run automatically without manual date selection in the UI | DELIVERED | Unspecified | 2026-07-17 | NO | 2026-07-17
Himaya Perumal | Understand what the manager (Iyappan) needs from the training assistant, write specific manager prompts, refine them, and test across multiple scenarios | GIVEN | Unspecified | - | NO | 2026-08-04
Himaya Perumal | change agent workflow design to use five separate agents | GIVEN | Unspecified | - | NO | 2026-07-28
Himaya Perumal | build an MCP server for the RAG system with authentication tokens for external service retrieval | DELIVERED | Unspecified | 2026-07-24 | NO | 2026-07-24
Himaya Perumal | Build and evaluate three agents on top of Dakshinya's code and infrastructure | IN_PROGRESS | Unspecified | - | NO | 2026-08-12
Himaya Perumal | Study Git and GitHub fundamentals, including purpose, commit workflows, upstream remotes, pushing, pulling, and stash/pop operations | GIVEN | Unspecified | - | NO | 2026-07-14

## Concept Gaps & Gaps
Trainee | Concept / Topic | Understanding State | Observation & Gap Notes | Session Date
Dakshinya Nachimuthu | Custom reranking weights vs metadata filtering | PARTIAL | Constructed 4 evaluation pipelines using custom reranking, but had difficulty justifying giving high reranker weights to metadata fields already filtered by Qdrant while keeping keyword density at 0.05 | 2026-08-12
Dakshinya Nachimuthu | Vector database metadata and filtering | CONFUSED | Dakshinya explicitly asks for clarification on metadata, stating that she is confused about how it works. | 2026-07-30
Dakshinya Nachimuthu | Metadata filtering | CONFUSED | Stated she did not understand metadata filtering correctly and was confused about it. | 2026-07-30
Himaya Perumal | Prompt structure (Identity, Knowledge, Actions) | PARTIAL | Himaya explains prompt rules and scenario handling, after which Siddharth formalizes prompt engineering into identity, domain knowledge, and instructions. | 2026-07-30
Himaya Perumal | Re-ranking | CONFUSED | Stated she was confused about how re-ranking works and asked for an explanation. | 2026-07-30
Dakshinya Nachimuthu | Context window scaling and batch size configuration | CONFUSED | Incorrectly claimed DeepSeek and LLaMA have the same context window and did not adjust batch size when switching models. | 2026-07-29
Himaya Perumal | Metadata filtering vs caching for RAG cost reduction | PARTIAL | Understood embedding caching for saving cost, but mistakenly believed metadata filtering reduces LLM token costs rather than aiding retrieval speed. | 2026-07-28
Himaya Perumal | RAG and vector database metadata | PARTIAL | Recognized vector embeddings are stored in Qdrant but was unable to clearly define metadata and retrieval mechanics when prompted. | 2026-07-28
Himaya Perumal | RAG cost reduction mechanisms | PARTIAL | Understood embedding caching reduces cost, but incorrectly believed metadata filtering reduces LLM token costs. | 2026-07-28
Dakshinya Nachimuthu | LangGraph graph model vs workflow | PARTIAL | Presented a standard workflow diagram missing supervisor agents and the full unified graph model representation | 2026-07-27
Himaya Perumal | API hosting and system access (FastAPI vs MCP) | CONFUSED | Believed external system access occurs only via MCP or Git and could not explain why FastAPI was used | 2026-07-27
Himaya Perumal | MCP deployment and multi-tenant access | CONFUSED | Assumed client users would connect to a locally hosted MCP server with tokens, failing to account for how external users access the system without local installation | 2026-07-27
Himaya Perumal | Embedding caching and cache hits | CONFUSED | Showed file sizes instead of cache hit metrics and confused prompt caching and KV caching with embedding caching. | 2026-07-23
Dakshinya Nachimuthu | LLM prompt instructions for handling missing context and hallucination prevention | CONFUSED | Dakshinya confused keyword scoring in retrieval with system prompt instructions controlling LLM hallucination when context is absent. | 2026-07-22
Himaya Perumal | Document chunking vs single-chunk embedding in RAG | CONFUSED | Himaya claimed token limits prevent accommodating an entire meeting transcript as a single chunk and showed uncertainty about how whole-document embedding affects retrieval. | 2026-07-22
Himaya Perumal | Embedding Caching | CONFUSED | Cached user input instead of document embeddings, confusing embedding caching with KV caching | 2026-07-22
Dakshinya Nachimuthu | Dense vs Sparse embedding models | CONFUSED | Loaded both dense and sparse models in the pipeline script without understanding the difference or purpose of sparse embeddings. | 2026-07-21
Dakshinya Nachimuthu | Topic shift detection in transcript chunking | CONFUSED | Claimed topic shift detection could not be used because a meeting only has one topic, overlooking that individual speaker turns and tasks constitute distinct sub-topics. | 2026-07-21
Dakshinya Nachimuthu | Re-ranking | PARTIAL | Acknowledges having surface-level knowledge of re-ranking but does not know it in depth. | 2026-07-21
Dakshinya Nachimuthu | Scroll API for chunk retrieval | CONFUSED | Incorrectly stated that retrieval without the Scroll API would return all chunks, requiring Siddharth to clarify that the Scroll API is what enables full retrieval. | 2026-07-21
Dakshinya Nachimuthu | system architecture 6 pillars and AI agent ownership | PARTIAL | Read through the document and understood the pillars have distinct graphs, but still working through what each pillar does and questioned why separate LLM instances are required. | 2026-07-20
Dakshinya Nachimuthu | LangGraph supervisors and agent architecture | PARTIAL | Dakshinya identified routing and validation agents but misidentified context manager as an agent and showed confusion regarding how the FME supervisor affects graph execution | 2026-07-17
Dakshinya Nachimuthu | LLM prompt construction | PARTIAL | Understood prompts conceptually as instructions, but did not articulate the mechanism of building structured dynamic prompts via dedicated functions | 2026-07-17
Himaya Perumal | MCP data retrieval methods | PARTIAL | Struggled to identify the method used to retrieve data from MCP server, initially confusing the FastMCP package and SQL connection before naming get commands | 2026-07-17
Dakshinya Nachimuthu | LLM prompt construction and execution | CONFUSED | Believed the prompt was created automatically by the LLM without explicit input until searching the codebase and finding the prompt context payload definition in the reasoning module. | 2026-07-16
Himaya Perumal | Supabase database connection and authentication | PARTIAL | Recognized API and project key credentials, but needed guidance on connection strings, password setup, and custom MCP client configuration. | 2026-07-16
Himaya Perumal | Supabase database connection methods | PARTIAL | Struggled to show the script querying Supabase and needed prompting on connection methods before identifying API | 2026-07-16
Dakshinya Nachimuthu | AI agent orchestration | PARTIAL | Described orchestration as combining tools step-by-step into a single agent, but had difficulty explaining full structural distinctions | 2026-07-15
Ganesh Krishna | AI agent harness | PARTIAL | Identified components of a harness including model codes, tool codes, MCPs, and bash commands | 2026-07-15
Ganesh Krishna | Excel formatting and cell coordinates vs database storage | CONFUSED | Proposed storing Excel coordinates in a database to query via SQL for LLM editing, but was unable to resolve how multi-cell header spans or formatting would be preserved or identified. | 2026-07-14
Himaya Perumal | Git version control and stash/pop mechanics | PARTIAL | Demonstrated understanding of basic push and commit status commands, but struggled to explain the purpose of GitHub, upstream forks, and git stash/pop. | 2026-07-14
Dakshinya Nachimuthu | Model Context Protocol (MCP) purpose and functionality | PARTIAL | Identified MCP as the tool/protocol to connect to external systems/hosts, but could not articulate the specific architectural problem MCP solves. | 2026-07-13
Dakshinya Nachimuthu | Agent schema handling and retrieval | PARTIAL | Mistook schema retrieval for schema creation, prompting mentor clarification on fetching schema from prompt context | 2026-07-13
Dakshinya Nachimuthu | MCP authentication and API endpoint access | PARTIAL | Recognized MCP's authentication and API access roles after questioning, but struggled initially to articulate its core architectural purpose. | 2026-07-13
Ganesh Krishna | AI Agent Orchestration Frameworks | PARTIAL | Acknowledged knowing basic definitions of orchestration frameworks but lacking deep understanding of practical agentic execution and framework-level orchestration. | 2026-07-10
Himaya Perumal | sparse vs. dense embeddings | PARTIAL | Correctly identified TF-IDF as sparse, but did not recognize or articulate that Nomic embeddings are dense. | 2026-07-08
Dakshinya Nachimuthu | model training metrics and learning curve validation | CONFUSED | Dakshinya's training curve showed a training score/accuracy of 1.0 across all samples, which Siddharth pointed out indicates an issue or lack of learning | 2026-07-03
Himaya Perumal | t-SNE dimensionality reduction | CONFUSED | Assumed t-SNE target dimension count is determined by dataset column count rather than feature space reduction for visualization. | 2026-07-02

## Decisions Register
Session Date | Owner | Decision | Rationale | Scope
2026-08-18 | Siddharth Saminathan | Push normalized transcripts into cloud Qdrant as a separate collection alongside the original unnormalized collection | Allows evaluating and using both collections to see whether normalized text or original transcript depth gives better retrieval results | Qdrant vector database / transcript collections
2026-08-18 | Siddharth Saminathan | Store structured events, QA, assignments, and patterns in a knowledge base DB instead of querying raw transcripts directly | To enable agents to retrieve structured event and question data without relying on raw transcript search | knowledge base architecture
2026-08-18 | Siddharth Saminathan | Structure session memory files (memory.md) to contain a per-session summary and per-session delta | To capture longitudinal trainee progress and delta over time without duplicating detailed event stores | session digest and memory design
2026-08-17 | Dakshinya Nachimuthu | Structure the RAG system into three modular services wrapped in FastAPI: Ingestion/Vector store (Qdrant), Retrieval service (with modular re-ranking and prompt builder), and Evaluation | Separates concerns so that teammates can consume the normalizer/ingestion and retrieval endpoints via API calls without exposing underlying experimental implementations or hardcoded logic | RAG architecture and backend service boundaries
2026-08-17 | Siddharth Saminathan | Himaya will build agent capabilities on top of Dakshinya's shared RAG pipeline and Ganesh's knowledge base rather than creating a separate retrieval or knowledge base engine | The underlying RAG retrieval and knowledge base code is owned and maintained by teammates; the agent layer is where Himaya's orchestration and persona definitions belong | Agent system architecture
2026-08-12 | Dakshinya Nachimuthu | Implement attention anchoring in Pipeline 4 by placing the user query at both the start and end of the input context. | Mitigates attention decay and maintains prompt adherence when processing large (~300k token) context documents. | Pipeline 4 MapReduce summarization
2026-08-04 | Siddharth Saminathan | Implement an LLM-based transcript normalization step to identify speaker roles and resolve speech ambiguities prior to chunking and RAG ingestion | Mitigate data quality and speaker ambiguity issues from Teams transcripts so RAG retrieval yields reliable information | Transcript processing and RAG ingestion pipeline
2026-08-04 | Siddharth Saminathan | Introduce an LLM normalization stage before RAG ingestion to resolve transcript speaker ambiguity and attribution | Audio mic bleed causes cross-speaker misattributions in transcripts, which is an upstream data quality problem that cannot be fixed at the RAG retrieval layer | transcript RAG ingestion pipeline
2026-07-31 | Siddharth Saminathan | System architecture diagrams must depict system boundaries, inputs, outputs, consumers, and data flow, keeping tech stack components (such as LangGraph, FastAPI, and PostgreSQL) in a separate tech stack section. | Tech stack tools like LangGraph are implementation details rather than core system architecture. | presentation and system architecture design
2026-07-30 | Siddharth Saminathan | Schedule training syncs weekly instead of daily. | To give trainees time to digest concepts, implement tasks, and bring specific questions when they encounter issues. | AI/ML training session cadence
2026-07-29 | Siddharth Saminathan | Use native Qdrant vector search rather than client-side PyTorch cosine similarity for vector retrieval | Client-side cosine similarity causes high latency, CPU/GPU throttling, and computational overhead compared to Qdrant native search | Retrieval experiment pipeline
2026-07-29 | Ganesh Krishna | Use file backup comparisons to track and display row-level Excel diffs (old row vs new row) instead of relying on Git diffs on binary Excel files | Git treats Excel files as binary and cannot produce meaningful line or cell-level diffs, whereas comparing saved backups per edit allows tracking specific changes | Excel file editing and diff rendering workflow
2026-07-28 | Siddharth Saminathan | Stream crisis resource numbers dynamically and render them in the UI instead of allowing the LLM to output phone numbers directly | Model training data becomes outdated and crisis phone numbers can change, risking the LLM hallucinating or providing defunct emergency contact numbers | Safety and crisis handling system architecture
2026-07-28 | Siddharth Saminathan | Isolate agent Excel editing inside a sandbox environment preserving the original file on disk and rendering diffs | To prevent unauthorized or broken direct modifications on the disk and enable safe autonomous agent file editing and diff rendering | Excel agent architecture
2026-07-28 | Siddharth Saminathan | Structure agent architecture with five separate agents rather than a single shared trainee agent | A single shared agent across all trainees risks exposing individual evaluation mistakes and feedback inappropriately in a professional training environment | trainee agent workflow architecture
2026-07-28 | Siddharth Saminathan | Use user-scoped metadata filtering in Qdrant for conversation memory and transcript retrieval instead of deploying separate agents per user | Allows a single agent system to isolate user transcripts and conversation histories by compulsory filtering on user ID | Agent architecture and vector store memory structure
2026-07-28 | Siddharth Saminathan | Use Scroll API as the primary retrieval approach for semantic search and document reading instead of relying solely on standard top-K chunk retrieval | Scrolling through the entire document or section-by-section allows retrieving top chunks across pages, resulting in higher precision and more comprehensive results | Retrieval pipeline / RAG architecture
2026-07-27 | Siddharth Saminathan | Store uploaded Excel structures and data in a database (DRM layer) at runtime to enable context retrieval without re-uploading | Prevents redundant user uploads by enabling search tools to look up previously mentioned documents directly from the database | Excel agent data storage and retrieval architecture
2026-07-23 | Siddharth Saminathan | Create and activate a virtual environment and maintain a requirements.txt file whenever developing and running Python code | To maintain engineering discipline and ensure code is usable and reproducible by others | entire team / Python development
2026-07-21 | Siddharth Saminathan | Store API keys exclusively in environment variables and ensure they are added to .gitignore rather than hardcoding them in scripts | Standard engineering discipline to protect API keys from exposure and prevent credential leakage in Git | All training scripts and repository commits
2026-07-21 | Siddharth Saminathan | Use dense embedding models instead of sparse models | Sparse models are unnecessary for this embedding pipeline setup | vector embedding and retrieval pipeline
2026-07-21 | Siddharth Saminathan | Avoid using standard LLM-based re-rankers and build a custom retrieval and re-ranking strategy tailored to the training transcripts and documents. | LLM-based re-rankers are generic, whereas a custom strategy allows leveraging specific domain knowledge of the documents. | retrieval and re-ranking pipeline
2026-07-17 | Ganesh Krishna | Use a single agent with three tool calls to handle user intent and building operations for the Excel workflow | One agent understands user intent and dispatches the appropriate tool calls | Excel agent architecture
2026-07-16 | Siddharth Saminathan | Build a custom MCP for Supabase to allow the agent to authenticate and retrieve data directly | Supabase does not provide a built-in custom MCP dropdown for their agent client setup, requiring a custom local MCP wrapper around the DB connection and auth | Agent architecture and Supabase database integration
2026-07-15 | Siddharth Saminathan | Add source metadata directly to the generated JSON fields during agent execution rather than running a post-processing reasoning agent step | Avoids needing an extra post-generation step and ensures the final JSON immediately identifies the source (RAG, internal RAG, DRM) | agent workflow JSON output schema
2026-07-14 | Dakshinya Nachimuthu | Adopt Option A (sentence-level tagging of provenance spans during workflow) rather than Option B (post-hoc evaluation of the final report) | Option B requires generating the response and then regenerating the JSON file, while Option A tracks tags directly on each sentence. | response provenance agent architecture
2026-07-13 | Siddharth Saminathan | Use Supabase (PostgreSQL) for database requirements across use cases | Provides multiple access interfaces (Python DB URL, MCP, REST API, SQL editor) and a free tier | Project database infrastructure
2026-07-13 | Siddharth Saminathan | Split the data analysis system into three distinct sub-agents: Data Engineer, Planner, and Business Analyst | Establishes clear single-responsibility boundaries for data extraction, query planning/schema preparation, and final analytical interpretation | Agent system architecture
2026-07-10 | Siddharth Saminathan | Focus current training and agent development on basic tool calls in LangChain/LangGraph, deferring MCPs and advanced memory layers to next week | Trainees should master basic agent tool execution first rather than getting bogged down by MCPs and complex memory persistence/validation layers | Training curriculum and practical agent implementation
2026-07-03 | Ganesh Krishna | Include threshold optimization for Random Forest as a key next step in the presentation | To optimize the decision cutoff threshold for probability values in Random Forest | Ganesh Krishna's Random Forest modeling next steps
2026-07-03 | Himaya Perumal | Use Keras instead of PyTorch for transfer learning and autoencoder next steps | Transfer learning is easier to implement in Keras than PyTorch | Spam filter autoencoder implementation
2026-07-02 | Himaya Perumal | Use TF-IDF instead of CountVectorizer for text vectorization | TF-IDF weights word importance rather than just counting frequency, aiding spam detection | Spam classification data preprocessing
2026-07-02 | Himaya Perumal | Use K-means clustering instead of DBSCAN | DBSCAN requires difficult parameter tuning | Unsupervised spam/ham message clustering